# AIHE-AE — AI-HED Completeness and Decision-Quality Review

Current digital location: Resource Set D — Procurement, Implementation, and Lifecycle Governance. Stable resource ID retained for continuity across companion editions.

Synthetic worked example

| Current digital location | Resource Set D — Procurement, Implementation, and Lifecycle Governance |
| --- | --- |
| Related book chapters | Chapter 12: Decision Architecture and Lifecycle Governance; Chapter 12: Decision Architecture and Lifecycle Governance; Chapter 12: Decision Architecture and Lifecycle Governance |
| Workflow step | 09: 09_Dossier_Decision |
| Version | 6.0.0 ¦ aligned to the fifteen-chapter reference edition and Resource Sets A–E |

Purpose. Review dossier completeness, confidence, inconsistencies, mandatory safeguards, decision readiness, and remediation.

Use note. Use the resource as a versioned institutional record. Adapt it to local law, policy, clinical practice, information security, procurement, and health-technology-assessment requirements. Do not enter identifiable patient data or confidential credentials into public copies.

Worked-example status. All names, organizations, figures, findings, and decisions are fictional and are included only to demonstrate completion logic.

# How to use this resource

This institutional review replaces the former grading-oriented dossier rubric. It tests completeness, internal consistency, confidence, mandatory safeguards, and decision readiness; it is not a student score.

# AI-HED completeness and decision-quality review

| Domain | Minimum decision-quality requirement | Status | Confidence | Critical gap or inconsistency | Action / owner / due |
| --- | --- | --- | --- | --- | --- |
| Decision problem and comparator | Measurable problem, intended use, excluded use, realistic alternatives, decision rule. | Complete | High | None. | Maintain through change control. |
| Data readiness and governance | Sources, fitness, provenance, lawful basis, access, representativeness, continuity. | Conditional | Medium | One terminology map pending. | Data steward—before pilot. |
| Evidence and local validation | External appraisal, local performance, calibration, subgroups, human factors, workflow utility. | Complete | Medium | Rare-event uncertainty remains. | Monitor prospectively. |
| Economic analysis | TCAIO, benefit mechanism, BIA, CEA/NMB where relevant, uncertainty, distribution, opportunity cost. | Complete | Medium | Savings depend on adoption. | Service owner—90-day review. |
| Ethics, equity, privacy, security, trust | Rights, safeguards, residual risk, human alternative, accessibility, incident response. | Conditional | Medium | Patient notice requires usability test. | Patient relations—30 days. |
| Procurement and contract | Evidence, audit, updates, pricing, service levels, data rights, exit, liability, assurance. | Complete | High | None. | Verify at signature. |
| Implementation and workforce | Stage plan, workflow, training, competency, capacity, adoption, change support. | Complete | Medium | Night-shift training not complete. | Clinical educator—before launch. |
| Monitoring and lifecycle | Cadence, metrics, thresholds, incidents, material change, renewal, de-adoption. | Complete | High | None. | Monthly pilot review. |
| Decision record | Recommendation, conditions, owners, dissent, authority, review date, trigger events. | Complete | High | None. | Archive signed record. |

# Mandatory safeguards

| Safeguard | Pass / conditional / fail | Evidence and residual risk |
| --- | --- | --- |
| Patient safety | Pass | Clinical safety review and fallback tested. |
| Lawful and proportionate data use | Conditional | Final access approval pending. |
| Privacy and cybersecurity | Pass | Security testing complete; residual vendor risk accepted. |
| Equity and non-discrimination | Conditional | Prospective subgroup monitoring required. |
| Human oversight and accountability | Pass | Named owner, escalation, override, and pause authority. |
| Monitoring and ability to stop | Pass | Thresholds, rollback, and de-adoption plan tested. |

# Decision and review record

| Field | Guidance | Record |
| --- | --- | --- |
| Recommended status | Proceed / proceed with conditions / redesign / restrict / pause / replace / retire | Proceed with conditions |
| Mandatory safeguards | Safety, lawful data use, privacy/security, equity, human oversight, monitoring, ability to stop | Passed with two conditions |
| Material unresolved issues | Record gaps that could change the decision | Local subgroup sample remains small |
| Conditions, owners, and due dates | Link every condition to an accountable owner and verification date | Clinical safety lead—complete 90-day review |
| Decision authority and date | Named committee or executive authority | AI Governance Committee; 30 July 2026 |
| Next review or trigger event | Date and event-triggered review conditions | Monthly during pilot; immediate review after material update |