## Instructions
AIHE-EX10 — Workflow Change and Training Competency Log
Item | Guidance | Action | Privacy / governance note
Workflow step | Implementation Change and Workforce | Complete this resource at this step in the process. | Do not include identifiable patient data in public files.
Purpose | Track workflow changes, training completion, competency, role changes, and hidden work during implementation. | Use the Template sheet for live completion. | Keep local copies in approved institutional storage.
Expected output | Workflow adaptation and training record | Export or attach the completed workbook to the AI-HED dossier. | Review with the appropriate accountable owner.
Version | 2.0.0 | Last reviewed 2026-07-26. | Check for newer public release before use.

## Template
Section | Field | Response / evidence | Owner | Due date | Status | Evidence link / note
Workflow | Changed step |  | Project team |  | Not started
Role | Responsible role |  | Project team |  | Not started
Training | Training module |  | Project team |  | Not started
Competency | Competency check |  | Project team |  | Not started
Burden | Hidden work noted |  | Project team |  | Not started
Support | Support mechanism |  | Project team |  | Not started
Metric | Adoption indicator |  | Project team |  | Not started
Action | Corrective action |  | Project team |  | Not started

## Worked_Example
Section | Field | Response / evidence | Owner | Due date | Status | Evidence link / note
Workflow | Changed step | Risk review added to morning huddle | Project team | 2026-09-30 | In progress | Synthetic worked example
Role | Responsible role | Case manager | Project team | 2026-09-30 | In progress | Synthetic worked example
Training | Training module | AI output interpretation | Project team | 2026-09-30 | In progress | Synthetic worked example
Competency | Competency check | Scenario-based quiz completed | Project team | 2026-09-30 | In progress | Synthetic worked example
Burden | Hidden work noted | Extra chart review for alerts | Project team | 2026-09-30 | In progress | Synthetic worked example
Support | Support mechanism | Super-user channel | Project team | 2026-09-30 | In progress | Synthetic worked example
Metric | Adoption indicator | Dashboard reviewed daily | Project team | 2026-09-30 | In progress | Synthetic worked example
Action | Corrective action | Simplify alert wording | Project team | 2026-09-30 | In progress | Synthetic worked example

## Data_Dictionary
Sheet | Variable | Type | Allowed values / units | Description | Example
Template | Changed step | text | Free text or evidence link | Changed step | Risk review added to morning huddle
Template | Responsible role | text | Free text or evidence link | Responsible role | Case manager
Template | Training module | text | Free text or evidence link | Training module | AI output interpretation
Template | Competency check | text | Free text or evidence link | Competency check | Scenario-based quiz completed
Template | Hidden work noted | text | Free text or evidence link | Hidden work noted | Extra chart review for alerts
Template | Support mechanism | text | Free text or evidence link | Support mechanism | Super-user channel
Template | Adoption indicator | text | Free text or evidence link | Adoption indicator | Dashboard reviewed daily
Template | Corrective action | text | Free text or evidence link | Corrective action | Simplify alert wording