## Instructions
Digital Resource AIHE-Q: GATED-AI Gate Record
Resource ID | AIHE-Q
Version | V1.0
Last reviewed | 2026-07-26
Related chapters | Chapters 12 and 18
Intended users | Students, instructors, hospital managers, clinicians, health economists, informatics, governance, and project teams
Status | Educational and practice-support instrument
Privacy | Do not enter identifiable patient information, credentials, or confidential vendor data.
Instructions | Complete yellow cells; preserve formulas; record evidence, assumptions, owners, dates, thresholds, and local adaptations.

## S1T1_Main_Blank
Gate | Required evidence submitted | Status | Conditions / remediation | Owner | Due date | Decision signature
G0 Problem
G1 Evidence
G2 Data and infrastructure
G3 Economics and affordability
G4 Ethics, equity, privacy, and oversight
G5 Workflow, workforce, and implementation
G6 Contract and vendor
G7 Monitoring, updates, and exit

## S1T1_Main_Worked
Gate | Required evidence submitted | Status | Conditions / remediation | Owner | Due date | Decision signature
G0 Problem | Illustrative response for G0 Problem: evidence documented, limitations noted, and an accountable owner assigned. | Conditional |  | Named project owner | 2026-10-01 | Proceed to a limited pilot with conditions and predefined stopping rules.
G1 Evidence | Illustrative response for G1 Evidence: evidence documented, limitations noted, and an accountable owner assigned. | Conditional |  | Named project owner | 2026-10-01 | Proceed to a limited pilot with conditions and predefined stopping rules.
G2 Data and infrastructure | Illustrative response for G2 Data and infrastructure: evidence documented, limitations noted, and an accountable owner assigned. | Conditional |  | Named project owner | 2026-10-01 | Proceed to a limited pilot with conditions and predefined stopping rules.
G3 Economics and affordability | Illustrative response for G3 Economics and affordability: evidence documented, limitations noted, and an accountable owner assigned. | Conditional |  | Named project owner | 2026-10-01 | Proceed to a limited pilot with conditions and predefined stopping rules.
G4 Ethics, equity, privacy, and oversight | Illustrative response for G4 Ethics, equity, privacy, and oversight: evidence documented, limitations noted, and an accountable owner assigned. | Conditional |  | Named project owner | 2026-10-01 | Proceed to a limited pilot with conditions and predefined stopping rules.
G5 Workflow, workforce, and implementation | Illustrative response for G5 Workflow, workforce, and implementation: evidence documented, limitations noted, and an accountable owner assigned. | Conditional |  | Named project owner | 2026-10-01 | Proceed to a limited pilot with conditions and predefined stopping rules.
G6 Contract and vendor | Illustrative response for G6 Contract and vendor: evidence documented, limitations noted, and an accountable owner assigned. | Conditional |  | Named project owner | 2026-10-01 | Proceed to a limited pilot with conditions and predefined stopping rules.
G7 Monitoring, updates, and exit | Illustrative response for G7 Monitoring, updates, and exit: evidence documented, limitations noted, and an accountable owner assigned. | Conditional |  | Named project owner | 2026-10-01 | Proceed to a limited pilot with conditions and predefined stopping rules.

## S1T2_Main_Blank
Vendor claim | Evidence provided | Independent verification | Local applicability | Risk if incorrect | Contract representation / remedy
Clinical or operational performance
Time or productivity savings
Cost savings / ROI
Subgroup fairness
Interoperability
Cybersecurity and uptime
Explainability / human oversight
Update and monitoring capability

## S1T2_Main_Worked
Vendor claim | Evidence provided | Independent verification | Local applicability | Risk if incorrect | Contract representation / remedy
Clinical or operational performance | Illustrative response for Clinical or operational performance: evidence documented, limitations noted, and an accountable owner assigned.
Time or productivity savings | Illustrative response for Time or productivity savings: evidence documented, limitations noted, and an accountable owner assigned.
Cost savings / ROI | Illustrative response for Cost savings / ROI: evidence documented, limitations noted, and an accountable owner assigned.
Subgroup fairness | Illustrative response for Subgroup fairness: evidence documented, limitations noted, and an accountable owner assigned.
Interoperability | Illustrative response for Interoperability: evidence documented, limitations noted, and an accountable owner assigned.
Cybersecurity and uptime | Illustrative response for Cybersecurity and uptime: evidence documented, limitations noted, and an accountable owner assigned.
Explainability / human oversight | Illustrative response for Explainability / human oversight: evidence documented, limitations noted, and an accountable owner assigned.
Update and monitoring capability | Illustrative response for Update and monitoring capability: evidence documented, limitations noted, and an accountable owner assigned.

## S1T3_Main_Blank
Contract requirement | Included? | Clause / location | Gap / negotiation position | Owner
Approved intended use and version
Evidence and audit rights
Update notice, validation, approval, rollback
Data use, retention, portability, deletion
Cybersecurity, vulnerability, incident notification
Service levels, support, downtime, continuity
Price, escalation, interface and update costs
Subprocessors and material changes
Termination triggers and decommissioning support

## S1T3_Main_Worked
Contract requirement | Included? | Clause / location | Gap / negotiation position | Owner
Approved intended use and version |  |  |  | Named project owner
Evidence and audit rights |  |  |  | Named project owner
Update notice, validation, approval, rollback |  |  |  | Named project owner
Data use, retention, portability, deletion |  |  |  | Named project owner
Cybersecurity, vulnerability, incident notification |  |  |  | Named project owner
Service levels, support, downtime, continuity |  |  |  | Named project owner
Price, escalation, interface and update costs |  |  |  | Named project owner
Subprocessors and material changes |  |  |  | Named project owner
Termination triggers and decommissioning support |  |  |  | Named project owner