## Instructions
Digital Resource AIHE-R: VALIDATE-AI Implementation Plan
Resource ID | AIHE-R
Version | V1.0
Last reviewed | 2026-07-26
Related chapters | Chapters 15 and 18
Intended users | Students, instructors, hospital managers, clinicians, health economists, informatics, governance, and project teams
Status | Educational and practice-support instrument
Privacy | Do not enter identifiable patient information, credentials, or confidential vendor data.
Instructions | Complete yellow cells; preserve formulas; record evidence, assumptions, owners, dates, thresholds, and local adaptations.

## S1T1_Main_Blank
Stage | Objectives | Activities | Measures | Acceptance criteria | Owner | Decision / date
V Verify problem
A Assess readiness
L Local validation
I Implement pilot
D Determine value
A Adapt governance
T Transition to scale
E Evaluate continuously

## S1T1_Main_Worked
Stage | Objectives | Activities | Measures | Acceptance criteria | Owner | Decision / date
V Verify problem |  |  |  |  | Named project owner | Proceed to a limited pilot with conditions and predefined stopping rules.
A Assess readiness |  |  |  |  | Named project owner | Proceed to a limited pilot with conditions and predefined stopping rules.
L Local validation |  |  |  |  | Named project owner | Proceed to a limited pilot with conditions and predefined stopping rules.
I Implement pilot |  |  |  |  | Named project owner | Proceed to a limited pilot with conditions and predefined stopping rules.
D Determine value |  |  |  |  | Named project owner | Proceed to a limited pilot with conditions and predefined stopping rules.
A Adapt governance |  |  |  |  | Named project owner | Proceed to a limited pilot with conditions and predefined stopping rules.
T Transition to scale |  |  |  |  | Named project owner | Proceed to a limited pilot with conditions and predefined stopping rules.
E Evaluate continuously |  |  |  |  | Named project owner | Proceed to a limited pilot with conditions and predefined stopping rules.

## S1T2_Main_Blank
Pilot element | Specification
Site, service, population, dates
System, version, intended use, excluded uses
Comparator / baseline
User groups and training / competence requirement
Human review and decision authority
Primary effectiveness and safety outcomes
Workflow, economic, equity, and trust outcomes
Data collection and analysis plan
Incident response and authority to pause
Stopping rules
Pilot completion and scale criteria

## S1T2_Main_Worked
Pilot element | Specification
Site, service, population, dates | Illustrative response for Site, service, population, dates: evidence documented, limitations noted, and an accountable owner assigned.
System, version, intended use, excluded uses | Illustrative response for System, version, intended use, excluded uses: evidence documented, limitations noted, and an accountable owner assigned.
Comparator / baseline | Illustrative response for Comparator / baseline: evidence documented, limitations noted, and an accountable owner assigned.
User groups and training / competence requirement | Illustrative response for User groups and training / competence requirement: evidence documented, limitations noted, and an accountable owner assigned.
Human review and decision authority | Illustrative response for Human review and decision authority: evidence documented, limitations noted, and an accountable owner assigned.
Primary effectiveness and safety outcomes | Illustrative response for Primary effectiveness and safety outcomes: evidence documented, limitations noted, and an accountable owner assigned.
Workflow, economic, equity, and trust outcomes | Illustrative response for Workflow, economic, equity, and trust outcomes: evidence documented, limitations noted, and an accountable owner assigned.
Data collection and analysis plan | Illustrative response for Data collection and analysis plan: evidence documented, limitations noted, and an accountable owner assigned.
Incident response and authority to pause | Illustrative response for Incident response and authority to pause: evidence documented, limitations noted, and an accountable owner assigned.
Stopping rules | Illustrative response for Stopping rules: evidence documented, limitations noted, and an accountable owner assigned.
Pilot completion and scale criteria | Illustrative response for Pilot completion and scale criteria: evidence documented, limitations noted, and an accountable owner assigned.

## S1T3_Main_Blank
Role | Required knowledge / skill | Training format | Competence evidence | Refresher trigger | Owner
Board/executive
Clinical users
Operational managers
Data/IT/security
Finance/economics/procurement
Ethics/privacy/quality
Support/help desk

## S1T3_Main_Worked
Role | Required knowledge / skill | Training format | Competence evidence | Refresher trigger | Owner
Board/executive |  |  | Illustrative response for Board/executive: evidence documented, limitations noted, and an accountable owner assigned. |  | Named project owner
Clinical users |  |  | Illustrative response for Clinical users: evidence documented, limitations noted, and an accountable owner assigned. |  | Named project owner
Operational managers |  |  | Illustrative response for Operational managers: evidence documented, limitations noted, and an accountable owner assigned. |  | Named project owner
Data/IT/security |  |  | Illustrative response for Data/IT/security: evidence documented, limitations noted, and an accountable owner assigned. |  | Named project owner
Finance/economics/procurement |  |  | Illustrative response for Finance/economics/procurement: evidence documented, limitations noted, and an accountable owner assigned. |  | Named project owner
Ethics/privacy/quality |  |  | Illustrative response for Ethics/privacy/quality: evidence documented, limitations noted, and an accountable owner assigned. |  | Named project owner
Support/help desk |  |  | Illustrative response for Support/help desk: evidence documented, limitations noted, and an accountable owner assigned. |  | Named project owner